## Slide 1: Planning the project activities and budget
INTERREG - IPA CBC Programme Bulgaria–Turkey
CCI 2014TC16I5CB005

## Slide 2: Planning the project activities
The activities are concrete actions to achieve planned results through utilization of the project budget.
steps
Specify the core activities and their components/ sub-activities;
Define the sequence of execution;
Reflect the timing for implementation of the activities into the time schedule;
Specify who is responsible for implementing the activities;
Formulate the necessary methods and resources to achieve them;
Describe the expected outputs.
tips
Check the eligible actions in the Guidelines for Applicants;
Ensure that all activities necessary to achieve the planned results are included;
Plan a time reserve for activities requiring subcontracting or a longer preparation period;
Check quantity, timing and place. This will help you prepare your budget.
The activities must be realistic, feasible and clearly linked to the budget..

## Slide 3: Structuring the activities in the application form
The activities can be mono-component (single action to achieve a goal) or multi-component.
The activity № depends on the planned sequence of execution of the activities;
Use the same title for each activity (including for sub-activities, if applicable) in all parts of the application form and budget;
The location (NUTS3) directs whether the activities are in the eligible region and in which partner(s)’ budget are envisaged the necessary expenditures;
The purpose of the description of the activities is to inform about the specific actions that will be taken to achieve planned objectives. Describe participants, quantities, numbers, exact location (city/ village), duration (days/months), purpose, link with other activities, etc.;
To identify a responsible partner depends on the type of the activity and the distribution of responsibilities;
The methods and resources direct to the necessary (in)tangible means of implementation of the activity (experts, supplies, services, materials, etc.);
The outputs give an idea of exactly what will be achieved after the implementation of the activity.
Project management, subcontracting, accounting, etc. should not be planned as separate activities. They are an integral part of the core activities.

## Slide 4: Filling-in the duration and action plan
The time table in section 2.6 of the application form (AF) summarizes the timing of implementation of the planned activities.
tips
Ensure that the time schedule is realistic and feasible;
Plan a time reserve for activities requiring sub-contracting or a longer preparation period or events scheduled at the beginning and end of the project;
In case of construction and repair work, leave a reserve of 1-2 quarters due to the seasonality of the work;
Planning of too many activities in one period is directly related to spending significant funds by the beneficiaries;
steps
    The described activities in section 2.3 of the AF and their sequence are automatically transferred to the table;
    Plan enough time for each activity and fill-in its duration in quarters in the time table;
    Keep in mind the sequence and the connection between the different activities. For example, “soft” activities related to the investment part should be planned after the completion of the works or the delivery of the supplies;
Changing the duration and action plan is the most common type of contract modification.
Ensure that the planned time for implementing the activities in section 2.3 meets the periods in section 2.6.
.

## Slide 5: description of soft activities - examples
Organization of events (seminar/ training/ press-conference, etc.):
Title of the event;
Purpose of the event and link with other project activities;
Duration and location;
Estimated number, background and nationality of participants;
Necessary equipment, logistics, materials, etc.;
Provision for catering and/ or accommodation to the participants;
Involvement of external experts – (lecturers, trainers, interpreters, consultants etc.);
Materials and consumables;
Responsible partner for the overall organization.
Elaboration of intellectual products (analyses/ researches, strategies, etc.):
Title;
Purpose of the event and link with other project activities;
Requirements for the content and justification;
Necessary resources (for example, number and type of experts involved and duration of their involvement);
Description of the expected product (hard copy, electronic version, number of pages, etc.), languages;
Reference to a technical specification with price breakdown of all components.

## Slide 6: description of investment activities - examples
Works/ renovation:
Title and description of the works, including reference to technical designs and estimated bills of quantities;
Description of the current situation of the site;
Purpose that the building/ premises/ object will serve after construction/ renovation.
Relations to other activities, i.e. soft activities or supplies demonstrating the way of use;
Provisions for design, permits, approvals at the stage of application, during the implementation and needed for the lawful completion and commissioning of the object, if applicable. The same applies to the supervision;
Provision for approved works design for the whole object or part of it, if applicable. The same applies to the environmental assessment.
Supplies (equipment, furniture, materials, etc.):
Description;
Exact quantities;
Purpose of the supplies (including link with other project activities);
Reference to a technical specification with price breakdown of all components and justification of the need for the supplies.

## Slide 7
The financial resources needed for the implementation of the activities previously described in details in the application form.
steps
Identify the financial resources needed to implement the activities;
Distribute them by budget lines and sub-lines;
Specify the type of units;
Determine the quantity you need;
Define the unit price;
Calculate the total cost.
Planning the project budget
tips
Ensure that expenditures are envisaged for all activities;
Make sure all prices are in euro and realistic;
Check the eligible and ineligible direct and indirect costs in the Guidelines;
Foresee a reasonable increase rate for deliveries and construction works;
Attach a detailed breakdown and justification for all total amounts.
The expenditures in the budget must be based on and clearly linked to the project activities.

## Slide 8: BUDGET LINES AND THRESHOLDS
The thresholds (min. and max. for BL5 and max. for BL1, BL2 and BL6 are obligatory and will be ground for rejection of the project proposal.
Budget lines |  | 
BL1 | Staff costs | “Soft” projects: max. 15% of direct costs “Investment” projects: max. 10% of direct costs
BL2 | Office and administrative costs | Max. 15% of BL1 Staff costs “Soft” and “Investment” projects
BL3 | Travel and accommodation costs | 
BL4 | External expertise and services costs | 
BL5 | Equipment and works | “Investment” projects: min. 50% of total eligible project costs “Soft” projects: max. 50% of total eligible project costs
BL6 | Project preparation | Max. 3% of direct project costs (BL3+BL4+BL 5) Max. € 3000 for “Preparation of Application package”

## Slide 9: type of expenditures
  The earliest possible starting date for eligibility of project expenditures is the date following the Subsidy contract registration in the Registry system of MA with the exception of expenditures for project preparation (when applicable).
direct: they can be attributed directly to the project (travel and accommodation, external expertise and services, equipment and works);
indirect: they cannot be assigned directly to the project activities but are necessary for their implementation (expenditures for staff, office and administrative expenditures);
Project preparation – they are carried out before the project implementation period.
BL3 + BL4 + BL5
BL1, BL2
BL6

## Slide 10: BUDGET LINE 1 Staff costs
Staff costs shall be reimbursed by the Managing authority to the beneficiaries as a flat rate:
max. 10% of direct costs for “investment” projects.
max. 15% of direct costs for “soft” projects;
The flat rate % should be indicated in the budget by the project partner and will remain the same for the entire project implementation period.
In the verification process the beneficiaries do not need to present supporting documents.

## Slide 11: BUDGET LINE 2 Office and administrative costs
Office and administrative costs shall be reimbursed by the Managing authority to the beneficiaries as a flat rate of max. 15% of BL1 for „soft“ and investment projects:
Rent of office
Overheads
Consumables
Bank charges
Maintenance costs
The flat rate % should be indicated in the budget by the project partner and will remain the same for the entire project implementation period.

## Slide 12: BUDGET LINE 3 Travel and accommodation costs
Expenses for the project staff members for
participation in events related to the project implementation:
  Travel costs - max. €0,21/km for fuel; €1,50/km for rent of vehicle
  Daily allowances - €20 in the eligible border region; €35 outside the eligible area
  Accommodation – up to €60 the eligible border region; up to €130 outside the eligible area
  Visa costs
Avoid overlapping of expenditures for daily allowances in the budget of the visiting organization and for catering - in the budget of the hosting organization. The max. thresholds and proposed units shall be observed.

## Slide 13: BUDGET LINE 4 External expertise and services costs
Expenses for organization of seminars, meetings, press-conferences, awareness campaigns, trainings, consultancy, studies, designs, etc.
  Rent of hall and equipment
  Coffee breaks, catering
  Consumables and materials
  Transportation and accommodation of participants
  Elaboration, design, translation
  Publications in mass-media
  Consultancy, studies, designs, website development, etc.
  Authorizations, certificates, etc.
  Interpreters, lecturers, trainers
  Others
Check the correspondence of the units and quantities planned in the activities and those – in the budget.
The proposed units shall be observed.

## Slide 14: Budget line 5 equipment and works
Small scale construction and supply, represents the
investment part of the project:
The eligible expenses of BL5 by investment projects – min. 50% of total eligible project costs.
The eligible expenses of BL5 by „soft“ projects - max. 50% of total eligible project costs.
The thresholds are obligatory.
Support all supplies and expenses planned as lump sum with technical specifications.

## Slide 15: Budget line 6 project preparation
Expenses for meetings between partners, consultancy, studies, feasibility studies, technical surveys, works design, certificates, permits, translation of documents, taxes, etc.):
The total costs for “Preparation of Application package” and “Preparation of technical documentation” - max. 3% of the direct project costs.
max. € 3000 for “Preparation of Application package”.
The project preparation expenditures should be carried out before or on the date of submission of the project proposals at the latest.
The cost for project preparation will be reimbursed only to those applicants awarded subsidy contracts.

## Slide 16: VAT and own co-financing
For Bulgarian partners, if the VAT is non-recoverable from other sources, it is eligible for financing by the Programme (letter of the Minister of finance № NF-3/ 23.12.2016).
Before filling the application form each beneficiary should clarify its VAT status for each activity and determine the VAT as recoverable or non-recoverable from other sources.
The applicants may provide own co—financing (it is not obligatory), which should be reflected in column “Own co-financing” of table 2 in the budget of the respective partner.
The own co-financing will be a subject of verification together with the other project expenditures.
In case VAT is eligible for financing it should be included by the applicant in the respective unit rates in his budget.
It is financial contribution of a partner that is not bound to a particular activity. In-kind contribution is not eligible expenditure!

## Slide 17: REVENUE GENERATING PROJECTS
            Commercial activities and other aiming at profit generation are not eligible under the Programme. In case the project generates revenue, the total eligible expenditures shall be reduced by the net revenue (Regulation (EU) 1303, Art. 65(8).
Net revenue of the operation means cash in-flows directly paid by users for goods or services provided by the operation (e. g. if project concerns renovation of sport facilities, revenues generated from tickets for using these sport facilities during project implementation should be reduced).
Beneficiaries should keep detailed, timely, adequate and traceable
information concerning the generated revenues.

## Slide 18: OMISSIONS WHEN PLANNING THE BUDGET
    The min. and max. grant amounts according to a Priority axis, specific objective and type of the project are not observed;
    The expenditures specified in the budget do not correspond to the planned activities and vice versa;
    There are no expenditures envisaged for all activities specified in the application form;
Unrealistic quantities of resources are envisaged (number of participants, km, information and publicity materials, etc.);
The expenditures are not budgeted in the correct budget line or there is overlapping;
The min. and max. thresholds of the respective budget lines are not observed;
The budget is not estimated on the basis of real market prices;
There are ineligible expenditures included.

## Slide 19: Planning information and publicity activities
  The project activities and results reach the target groups and final beneficiaries through the communication and visualization tools.
  Their good planning is essential for a successful project.
  STEPS
  Identify the main communication activities and tools by which you will promote the project, e.g. press-conferences, media publications, website, leaflets, brochures, billboards, advertising materials, social media activities, etc.;
  Describe them clearly in p. 2.5 "Communication and Visualization" of the application form (2.5.1 "Communication Strategy" and 2.5.2 "Communication tools"). Specify the responsible partners, target groups and the number of persons to be reached;
  TIPS
  The names of information activities and tools must be identical in all parts of the AF and budget;
  It is possible to plan a separate activity for information and publicity in p. 2.3 of the AF, but it is not obligatory. Publicity can also be described in the framework of the main project activities;
  Ensure that the information and publicity data described in p. 2.3 and p. 2.5 of the AF is fully identical in terms of content, types, quantity, users, etc.;
  Plan a realistic and feasible number of end-users of the publicity tools.

## Slide 20: Link between the information activities and the budget
  STEPS
  Identify the necessary material and human resources to carry out the planned information and publicity activities;
  Distribute the costs in the respective lines and sub-lines in each partner's budget;
  Describe the technical parameters of the information tools and materials in the budget - paper, size, colour, number of pages, languages, visualization, printing, design, publications, type of media, number of broadcasts, participants in info events, duration, etc. It this is not possible, attach a separate specification;
  TIPS
  Get acquainted with Regulation (EU) No 1303/2013, Annex XII, Article 2.2, laying down the mandatory information and publicity requirements;
  Make sure that there is full compliance between types, quantity and number of planned information and publicity activities and tools in the activity part of the project and in the budget;
  The expenditures for designing a project logo are ineligible under the Programme;
  Attach a specification with detailed technical characteristics, unit prices, number/ quantity and total value in € for all costs planned as a lump sum;
  Planning expenditures for the of communication and visualization activities and tools in the budget.

## Slide 21: CAPITALISATION OF THE PROJECT
  STEPS
  Involve all partners in the implementation of the project's communication strategy;
  Create a short project name or acronym related to the main project idea and the corresponding priority axis;
  Prepare a good and meaningful summary of the project in Bulgarian, Turkish and English, that will be attractive to the general public. Tell your story - what the project aims to, what its activities are, how they will be achieved and what will change for people in the cross-border region.
  TIPS
  Good examples of summaries can be found on the Programme's website – “Funded Projects “ section;
  A minimum requirement for the language of information and publicity materials is English and the language of the partner. In order to reach a larger audience, it is advisable to prepare them in three languages;
  If participating in a third country event (e.g. in a tourist fair in Europe), you may prepare materials in the local language.
  The project should contribute to improving the cross-border region.
  make it visible to the people through dissemination of its results and achievements.

## Slide 22
INTERREG - IPA CBC Programme Bulgaria–Turkey
CCI 2014TC16I5CB005
Thank you for the attention!
The Programme is co-financed by the European Union
  Darina Tosheva
  Monitoring and financial expert
  Joint Secretariat Haskovo