## Slide 1: Key aspects of project financial management
Working meeting with NA and CCP
Ankara, 1st & 2nd November 2018

## Slide 2: Projects are starting implementation! Now, what should they do in the financial management field?

## Slide 3
Support tools in TESIM’s platform
https://www.goforenicbc.eu/

## Slide 4
Support tools in TESIM’s platform
FINANCIAL MANAGEMENT KIT FOR PROJECT IMPLEMENTATION
Module 1 - sound financial management
Module 2 - risk management
Module 3 - Internal control
Module 4 - governance and fraud detection
Module 5 - cash-flow management
Module 6 - procurement
Module 7 - accounting
Module 8 - document keeping
Module 9 - national requirements
Module 10- state aid

## Slide 5
Which are the key elements in financial management?
Let’s look at them!
Which are the key elements?
5 keys to financial management
1. Careful budgeting
2. Rigorous external checks
3. Regular reporting
4. Effective internal control
5. Reasonable care

## Slide 6
10 challenges for financial managers
Selecting appropriate financial tools and techniques for managing projects;
Understanding the dynamics and principles involved in the use of EU funds;
Ensuring a good understanding of the contract requirements, including applicable rules at EU, programme and national levels;
Aligning procurement and contracting processes with the ENI CBC and programme applicable rules;
Building robust performance indicators and reporting system for effective decision-making;

## Slide 7
10 challenges for financial managers
Defining the information and documentation workflows, by developing, adapting and/or using appropriate information systems;
Implementing adequate risk management tools, needed to implement risk mitigation actions;
Ensuring the establishment of an appropriate internal control, including a governance system able to prevent irregularities and fraud;
Enhancing accountability of the project in front of the EU institutions, programme and national bodies
Preparing the project closure from the beginning of its implementation.

## Slide 8
There are different challenges throughout the cycle
Set-up of the system
Project implementation
Project closure
Open-to-control period
The project cycle goes beyond the project implementation and execution periods, as according to article 70 of the ENI CBC Implementing Rules, “[…] the beneficiaries shall keep all documents related to the programme or a project for five years from the date of payment of the balance for the programme. In particular they shall keep reports, supporting documents, as well as accounts, accounting documents and any other document relating to the financing of the programme (including all documents relating to the contract award) […]”, that is, at least until 2029.

## Slide 9
There are different challenges throughout the cycle
Set up of the system
Construct a project financial management system embedded in the existing systems, but compliant with the needs and requirements of the approved project
Operate the project system
Implement project financial management activities during all the implementation period
Close the project
Prepare final report
Manage the open-to-checks period
Keep relationship with all beneficiaries, so that a swift response can be given to eventual checks by EU or other competent bodies
Ensure the archiving of all supporting documents and backup of all information in IT systems
Launch the project with all beneficiaries

## Slide 10
Which kind of information is needed?
What type of info should I provide?
Type of info | Examples
Problem-solving information, so you can propose a feasible course of action to project managers | Cash shortage, due to a delay in the reception of the funds caused by inadequate reporting by one of the project beneficiaries
Attention-directing information, so you can highlight areas where the project managers needs to focus, in order to prevent shortcomings, which might hamper the project implementation | Important currency fluctuation affecting one or several beneficiaries
Score-card information, building a performance management tool with ad-hoc indicators, so that the project manager can keep track of the financial execution on a regular basis and use this information for decision-making | Through regular updates of financial execution by all beneficiaries, in comparison with the budget in force and the financial plan

## Slide 11: Sound financial management, what does it mean?

## Slide 12
In the context of EU funding…
In the context of EU funding, the concept of sound financial management must be understood as a legal provision of the Financial Regulation. We find 3 interconnected components of this principle:
Effectivenes, Efficiency & Economy
Evaluation
SMART indicators

## Slide 13
In the context of EU funding…
The legal definitions of the three principles are:
  The principle of economy requires that the resources used by the institution for the pursuit of its activities shall be made available in due time, in appropriate quantity and quality and at the best price.
  The principle of efficiency is concerned with the best relationship between resources employed and results achieved.
  The principle of effectiveness is concerned with attaining the specific objectives set and achieving the intended results.
Tips to ensure compliance with the principles | 
Economy | Plan the procurement of works, supplies and services, as well as the recruitment of staff. Use adequate procurement procedures, regardless of the amount, and take into account not only the legality, but also the choice of award criteria in accordance with this principle.
Efficiency | Link your accounting to the activities and results. Be able to specify the amount of resources devoted to each activity and output.
Effectiveness | Use your logical framework as a follow-up tool for the achievement of the results and their contribution to the objectives. Monitor and evaluate the project with the support of the defined results and output indicators on an on-going basis, either internally or externally.

## Slide 14
In the context of EU funding…
“Specific, Measurable, Achievable, Relevant and Timed (SMART) objectives shall be set […]” (Financial Regulation)
SPECIFIC
Not vague
MEASURABLE
Quantifiable
ACHIEVABLE
Possible to attain
RELEVANT
Tied to programme goals
TIMED-BOUND
Have a clear end-point

## Slide 15
In the context of EU funding…
“[…] The achievement of those objectives shall be monitored by performance indicators” (Financial Regulation)
RELEVANT
Tied to project goals
ACCEPTED
By concerned stakeholders
CREDIBLE
Easy to interpret by anyone
EASY
Feasible to monitor and collect
ROBUST
Not easily manipulated

## Slide 16
In the context of EU funding…
The concept of sound financial management foes far beyond the strictly financial aspects of project management, as it provides the link between the money spent, the outputs produced and the results attained.
It answers to the question: was it worth to finance this project?

## Slide 17: Which is the first step?

## Slide 18
What is internal control
The lack of internal control is one of the key risks to EU funds being spent efficiently and in conformity with contract requirements. Setting up adequate control systems is an essential task in the start-up phase of the project.
Internal control is defined as a process affected by an organization's structure, work and authority flows, people and management information systems, designed to help the organization accomplish specific goals or objectives.
Therefore, in the framework of an ENI CBC project contract, internal control has to be designed to provide reasonable assurance that:
The project is effective and efficient
Financial information is reliable
Contractual conditions are met
You may check the adequacy of your system with the check-lists in proposed by the Europeaid’s Financial Management Toolkit:
https://ec.europa.eu/europeaid/work/procedures/financial-management-toolkit_en.htm_en
Being currently adapted to ENI CBC by TESIM

## Slide 19
5 components in internal control
Key messages | What we can do
Ensure sufficient segregation of duties. No single transaction or chain of transactions is in the hands of a single person. | physical control of assets versus verification tasks (for example, cash custody versus cash reconciliation tasks); management tasks versus authorisation tasks (for example, following procurement procedures versus authorising the contract with the supplier); management tasks versus accounting tasks (for example, approving the purchase invoice versus accounting for it); accounting tasks versus payment tasks (for example, preparing payment versus signing the bank transfer order).
Foresee effective approval points. Approving also means checking. Appropriate authorisation procedures enhance controls. Identify approval points that are relevant to the project and assign responsibility for carrying out such tasks to the most appropriate individuals. | the team leader may be asked to approve the timesheets for the project staff; financial manager checks and approves all project supporting documents.
Some examples

## Slide 20: Let’s see one of these components!

## Slide 21
Why should projects introduce risk management?
By developing sound assumptions to the logical framework, the project designers identified the foundation of identification of risks and contingency plans.
Nevertheless, the risks cannot be simply assessed during the preparation of the proposal or at the beginning of the project; its management must be embedded in the usual procedures of the beneficiaries

## Slide 22
The process of risk management
Monitoring and review
Measure, monitor and report
Set the context
Identify stakeholders
Risk assessment
Identify the events
Response strategy
Decide on risk treatment
Set objectives
Develop the process
Evaluate the risks
Determine strategy for risk mitigation
Communicate and consult
Integrate results into decision-making process

## Slide 23
Some tools
Some examples of typical risks may be:
Failure in measuring performance
Failure to monitor implementation
Delays in procurement
Loss or misappropriation of funds
Difficulties in delivery of outputs
Inadequate skills of the project team
Failure to engage stakeholders
Low-quality reporting
Delays in receiving EU funds

## Slide 24
Some tools
Risk assessment matrix

## Slide 25
7 messages on risk
A project team cannot become a “fire-fighting” team struggling to repair failures that could have been prevented
Key messages | 
1 | Make risk management part of your project
2 | Identify risks early
3 | Communicate about risks
4 | Consider also the events which may improve the achievement of objectives, so you can seize the opportunities
5 | Clarify the ownership of the risks and the related monitoring, mitigating and response measures
6 | Register, analyse, prioritise and monitor risks
7 | Plan in advance the risk responses

## Slide 26: Our goal: a robust, sound and transparent financial management system!