## Slide 1: Joint Operational Programme Black Sea Basin 2014-2020 Training for NA and CCP on project implementation
Ankara, Turkey
1-2 November 2018

## Slide 2
Monitoring – frequency,
aspects which will be monitored

## Slide 3
Expectations from projects
Achievement of all project objectives and indicators
Concrete, visible and sustainable results
Sound financial management
Capitalization of project results

## Slide 4
Monitoring
An efficient and effective monitoring activity strongly depends on receiving and/or collecting timely, reliable and relevant information/data about the progress in the implementation of activities, outputs and outcomes achieved by the project. The information system for collecting, analysing and reporting information about activities, outputs and outcomes is at the core of the monitoring system.
In supporting the Beneficiaries, immediately after the contract signature, JTS will appoint a JTS monitoring officer for each project and shall inform the respective Lead Beneficiary accordingly. The JTS appointed officer shall be the direct contact person providing support to the Lead Beneficiary and/or Beneficiaries.

## Slide 5
Monitoring
Be sure that:
All Beneficiaries have a shared understanding of the project objectives, activities, outputs and expected results, the working plan and project budget;
All Beneficiaries have a good understanding of the rules and contractual obligations and their role and responsibilities in the project - The project will be more successful when all partner Beneficiaries feel equally involved;
Communication procedures, both internal and external, have been established;
Make all necessary arrangements for ensuring a proper internal monitoring and follow up, if needed, of the project implementation;
Management and control system has been established

## Slide 6
Monitoring
Lead Beneficiary with the support of all the project Beneficiaries:
Set up a shared, internet-based, information tool including the control of deadlines, activities, deliverables and indicators.
Requiring the project manager for each Beneficiary to submit a regular, short monitoring report to the Lead Beneficiary providing information about the progress being made in implementing the project.
Managing Authority (MA) and the Joint Technical Secretariat (JTS) :
Regular monitoring
Organizing site visits to projects;
Result Oriented Monitoring (ROM).

## Slide 7
Regular Monitoring
Checking upon progress in the implementation based on the information provided by the Lead Beneficiary in each progress, intermediate and final reports (information collected from eMS).
Notes: 7

## Slide 8
Monitoring On-site monitoring visits
Regular - one visit run by the JTS once in 12 months of project implementation
Final monitoring visits – for all projects, no later than the deadline agreed for analyzing the Final report
Special visits/on the spot checks – may take place at any moment. On the spot checks will be performed on the based of a risk analysis at the authorizing level for every interim/final request for payment

## Slide 9
Monitoring Main Aspects to be verified
Documents and record keeping on technical implementation
Resources and Project management
Effectiveness of action
Progress in the implementation of activities and outputs achievement – Work Plan and timeline/milestones
Target groups involvement in the project activities/feedback
Compliance with the communication and visibility rules
Risks and Problems/remedial actions required – need for amendments to the contract (extension, budget changes etc,)
How the Beneficiaries prepare to ensure sustainability of the project results

## Slide 10
Monitoring On-site visit
The monitoring visits will take place at the premises of the Lead Beneficiary, Beneficiaries and in any of the project location, preferably during project activities (e.g. training activities, fairs, exhibitions, etc.).
The Lead Beneficiary and Beneficiaries will be notified in due time as regards the on-site regular or final visits. They should agree with the proposed date of the visit, its duration and the working documents which will have to be prepared.
The visit report will be drawn up in 2 original documents; each one has to be signed by the grant Lead Beneficiary or Beneficiary and the representatives of the MA/JTS participating to the visit.
The Lead Beneficiary who receives a monitoring visit shall always inform all other project Beneficiaries on the outcomes of the monitoring visit, measures and recommendations of the JTS/MA.

## Slide 11
Result Oriented Monitoring
During these visits the performance of projects funded will be reviewed with a focus on the likelihood that results will be achieved and on the need for remedial action. ROM reports will also make recommendations to Lead Beneficiary and Beneficiaries in order to improve project implementation.
The main criteria to be addressed during the visits are: Relevance and Quality of design, Efficiency of implementation to date, Effectiveness to date, Impact Prospects and Potential sustainability. For each criterion a detailed list of questions will be provided before every mission.
https://ec.europa.eu/europeaid/sites/devco/files/rom-handbook-2017_en.pdf
Notes: 11

## Slide 12
Thank you for your attention!